## RETROSPECTIVE
SPRINT RETROSPECTIVE
SPRINT ID | START | STOP | KEEP | MORE | LESS
SP001 | Add User demo to product review process. | Extending the Daily Scrum meeting, max duration should be 15 mins. | Circulating Daily Scrum meeting notes on email. | Communications to the Project Board. | Nothing at present.
SP002 | Adding to the Deployment Plan at the end of each Sprint. | Nothing at present. | Doing User demos. | Nothing at present. | Reduce meetings that require the dev team.
SP003 | Review Communications Plan Template at start of each Sprint. | Adding user stories late in the sprint. | Updating the Deployment Plan. | More testing alongside development. | Nothing at present.
Note on C8: stakeholdermap.com: What the team will start doing.
Note on D8: stakeholdermap.com: What the team will stop doing.
Note on E8: stakeholdermap.com: Actions the team will keep doing.
Note on F8: stakeholdermap.com: Actions that need to be done more often.
Note on G8: stakeholdermap.com: Actions that the team will do less of in the next sprint.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION