## BURNDOWN_CHART
BURNDOWN CHART
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 500 | 500
1 | 50 | 35 | 450 | 465
2 | 50 | 22 | 400 | 443
3 | 50 | 50 | 350 | 393
4 | 50 | 45 | 300 | 348
5 | 50 | 49 | 250 | 299
6 | 50 | 32 | 200 | 267
7 | 50 | 40 | 150 | 227
8 | 50 |  | 100
9 | 50 |  | 50
10 | 50 |  | 0
Note on B8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on C8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on F8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## PROJECT_DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## INSTRUCTIONS
Instructions
Days
Change this to the timescale that you want to appear at the bottom of the chart (the x axis).
Goal or target
Enter the number of features/story points that you plan to achieve in each time period. This forms the yellow line showing goal velocity on the chart.
Done or actual
Record how many features/story points that you actually achieve.
Goal or target velocity
This is a calculated field that counts down the target points to zero (completion of the project). It forms the left side of the chart (the y axis).
Remaining
This is a calculated field that simply deducts Done from Remaining. It is the blue line showing the actual burndown rate on the chart.